## Performance in Initiating
Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
15/SW/0089 | 164916 | NHS Permission | Entyvio (vedolizumab) long-term safety study: An international observational prospective cohort study comparing vedolizumab to other biologic agents in patients with ulcerative colitis or Crohn’s Disease | 2015-10-07 | 2015-10-08 | Yes | 2015-10-13 | 1 | 5 | 6 | Yes
14/SC/0171 | 120104 | NHS Permission | A phase III double-blind placebo-controlled randomised trial assessing the effects of aspirin on disease recurrence and survival after primary therapy in common non-metastatic solid tumours | 2015-10-22 | 2015-10-22 | Yes | 2016-07-26 | 0 | 278 | 278 | No | [12 empty] | Y |  | Y |  |  |  |  | NHS Provider
12/WA/0374 | 98726 | NHS Permission | Hart: Hughes Abdominal Repair Trial | 2016-01-19 | 2016-01-25 | Yes | 2016-02-23 | 6 | 29 | 35 | Yes
14/SS/1043 | 142447 | NHS Permission | UNIRAD: Randomized, double-blind, multicentre phase III trial evaluating the safety and benefit of adding everolimus to adjuvant hormone therapy in women with poor prognosis, ER+ and HER2- primary breast cancer who remain free of disease after at least 1 year of adjuvant hormone therapy | 2016-01-27 | 2016-01-27 | Yes | 2016-03-18 | 0 | 51 | 51 | Yes
15/EM/0095 | 166503 | NHS Permission | ACELARATE: Acelarin first line randomised pancreatic study | 2016-03-10 | 2016-03-14 | No |  | 4 |  |  | No | [11 empty] | Y | [6 empty] | Issues over drug administration | Sponsor
13/SC/0154 | 112665 | NHS Permission | FAIT: A Randomised Controlled Trial of Surgical versus Non-Surgical Treatment of Femoroacetabular Impingement | 2016-04-29 | 2016-04-29 | Yes | 2016-07-19 | 0 | 81 | 81 | No | [14 empty] | Y |  |  |  |  | NHS Provider

## Performance in Delivering
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Reason For Closure Of Trial | Comments
None