## Performance in Initiating
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
19/NW/0025 | 253778 | Supported exercise training for men on ADT (WP 3) | Yes | 2019-10-01 | 17 | 15 | 32 | 2019-06-13 | 2019-08-30 | 2019-02-18 | 2019-09-24 | 2019-09-16 |  | 2019-10-01
17/LO/0334 | 214459 | FLO-ELA | Yes | 2020-02-03 | 97 | 116 | 213 | 2019-05-03 | 2019-07-05 | 2019-03-29 | 2019-08-22 | 2019-10-10 |  | 2019-12-03 | G - No patients consented |  | NHS Provider
19/YH/0276 | 258327 | HEMISPAIRE | No |  | 61 |  |  | 2019-07-30 | 2019-11-08 | 2019-11-01 | 2019-11-22 | 2019-01-08 |  | 2020-01-08 | G - No patients consented |  | NHS Provider
18/YH/0358 | 242342 | The Sunflower Study | Yes | 2019-10-07 | 8 | 46 | 54 | 2019-03-04 | 2019-08-14 | 2018-12-12 | 2019-08-14 | 2019-08-22 |  | 2019-09-10
19/YH/0316 | 251056 | Knee Incision Trial | No |  | 37 |  |  | 2018-07-06 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 2020-01-29 |  | 2020-02-07
20/EE/0101 | 281712 | Recovery Trial | Yes | 2020-04-16 | 3 | 21 | 24 | 2020-03-17 | 2020-03-23 | 2020-03-17 | 2020-03-23 | 2020-03-26 |  | 2020-04-06

## Performance in Delivering
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed | Maximum Number Of Patients Agreed | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comment
None